## Sheet1
Date | Weekday | Task | Section | Status
2026-03-01 | Sunday | De-Trending Analysis | Results | Done
2026-03-01 | Sunday | Orbital Period | Results | Done
2026-03-02 | Monday | Add Modeling Data to Methods | Methods | Done
2026-03-02 | Monday | Start Modeling Theory | Methods | Done
2026-03-03 | Tuesday | Finish Modeling Theory | Methods | Done
2026-03-04 | Wednesday | Modeling Results | Results | Done
2026-03-05 | Thursday | Start Discussion | Discussion | Done
2026-03-06 | Friday | Add Objective to I | Introduction | Done
2026-03-07 | Saturday | Modeling Results | Results | Done
2026-03-08 | Sunday | Finished Results | Results | Done
2026-03-09 | Monday | Write Discussion | Discussion | Done
2026-03-10 | Tuesday | Finish Discussion | Discussion | Done
2026-03-10 | Tuesday | Added SHAP | M, R | Done
2026-03-11 | Wednesday | Revise OD text | M
2026-03-11 | Wednesday | Review Methods | M
2026-03-12 | Thursday | Review M + R | M, R
2026-03-13 | Friday | Write Conclusion | Conclusion
2026-03-14 | Saturday | Finish Conclusion | Conclusion
2026-03-15 | Sunday | Review Acronyms | all
2026-03-15 | Sunday | Review I + M | I, M
2026-03-16 | Monday | Review R + D + C | R, D, C
2026-03-17 | Tuesday | Review Everything | all
2026-03-18 | Wednesday | Hand-In